## Section summary
Number | Section | Checked | Unchecked | Total
Global | Global preparation and definition of done | 12 | 4 | 16
1 | Release safety, production build, and privacy | 52 | 6 | 58
2 | Scientific model correctness and result consistency | 173 | 67 | 240
3 | FCS parsing, channel validity, metadata, and memory | 53 | 0 | 53
4 | Sessions, OPFS, reproducibility, and local-file security | 58 | 0 | 58
5 | HTML, CSS, UI state, plotting, and accessibility | 196 | 10 | 206
6 | Automated tests, browser compatibility, and developer workflow | 76 | 9 | 85
7 | Documentation, provenance, and maintainability | 20 | 12 | 32
8 | Suggested implementation order and dependency map | 9 | 16 | 25
9 | Final release and scientific-readiness gate | 1 | 15 | 16
10 | Completion record template | 0 | 0 | 0
Total | All checklist sections | 650 | 139 | 789

## Number then code
Number | Section | Code | Checked | Unchecked | Total
Global | Global preparation and definition of done | PREP | 12 | 4 | 16
Global | Global preparation and definition of done | SECTION TOTAL | 12 | 4 | 16
1 | Release safety, production build, and privacy | REL/PRIV shared | 14 | 3 | 17
1 | Release safety, production build, and privacy | PRIV | 8 | 2 | 10
1 | Release safety, production build, and privacy | REL | 23 | 1 | 24
1 | Release safety, production build, and privacy | BUILD | 7 | 0 | 7
1 | Release safety, production build, and privacy | SECTION TOTAL | 52 | 6 | 58
2 | Scientific model correctness and result consistency | SCI | 114 | 7 | 121
2 | Scientific model correctness and result consistency | VALID | 1 | 9 | 10
2 | Scientific model correctness and result consistency | GATE | 7 | 1 | 8
2 | Scientific model correctness and result consistency | STATE | 7 | 3 | 10
2 | Scientific model correctness and result consistency | PEAK | 4 | 3 | 7
2 | Scientific model correctness and result consistency | DOMAIN | 4 | 4 | 8
2 | Scientific model correctness and result consistency | QC | 36 | 10 | 46
2 | Scientific model correctness and result consistency | STAT | 0 | 5 | 5
2 | Scientific model correctness and result consistency | LEGACY | 0 | 7 | 7
2 | Scientific model correctness and result consistency | UNC | 0 | 7 | 7
2 | Scientific model correctness and result consistency | PERF-MODEL | 0 | 7 | 7
2 | Scientific model correctness and result consistency | FUTURE | 0 | 4 | 4
2 | Scientific model correctness and result consistency | SECTION TOTAL | 173 | 67 | 240
3 | FCS parsing, channel validity, metadata, and memory | DATA | 53 | 0 | 53
3 | FCS parsing, channel validity, metadata, and memory | SECTION TOTAL | 53 | 0 | 53
4 | Sessions, OPFS, reproducibility, and local-file security | SES | 34 | 0 | 34
4 | Sessions, OPFS, reproducibility, and local-file security | SEC | 24 | 0 | 24
4 | Sessions, OPFS, reproducibility, and local-file security | SECTION TOTAL | 58 | 0 | 58
5 | HTML, CSS, UI state, plotting, and accessibility | UI | 168 | 7 | 175
5 | HTML, CSS, UI state, plotting, and accessibility | PERF-UI | 22 | 3 | 25
5 | HTML, CSS, UI state, plotting, and accessibility | MAINT | 6 | 0 | 6
5 | HTML, CSS, UI state, plotting, and accessibility | SECTION TOTAL | 196 | 10 | 206
6 | Automated tests, browser compatibility, and developer workflow | CI | 65 | 2 | 67
6 | Automated tests, browser compatibility, and developer workflow | DEV | 5 | 0 | 5
6 | Automated tests, browser compatibility, and developer workflow | PLAT | 6 | 7 | 13
6 | Automated tests, browser compatibility, and developer workflow | SECTION TOTAL | 76 | 9 | 85
7 | Documentation, provenance, and maintainability | DOC | 16 | 6 | 22
7 | Documentation, provenance, and maintainability | MAINT | 4 | 6 | 10
7 | Documentation, provenance, and maintainability | SECTION TOTAL | 20 | 12 | 32
8 | Suggested implementation order and dependency map | PHASE | 9 | 16 | 25
8 | Suggested implementation order and dependency map | SECTION TOTAL | 9 | 16 | 25
9 | Final release and scientific-readiness gate | SECTION TOTAL | 1 | 15 | 16
10 | Completion record template | SECTION TOTAL | 0 | 0 | 0